## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 |  | 2024-11-14 | for yolo model training system crashes with cpu | s1 |  | Maintainability | GPU based | 2024-11-14 | closed
2 |  | 2024-11-16 | object detection model accuracy is low | s1 |  | Standards | trained on large dataset | 2024-11-16 | closed
3 |  | 2024-11-28 | not figuring out the best ocr | s2 |  | Standards | using image ocr | 2024-11-28 | closed
4 |  | 2024-11-29 | installation of imageocr | s3 |  | Maintainability | checking with python and tensorflow version | 2024-11-29 | closed
5 |  | 2024-12-05 | annoting licensenumber | s4 |  | Logical | subtraction of the coordinates | 2024-12-06 | closed
6 |  | 2025-12-26 | getting class in visualize script | s4 |  | Logical | using the direct method rather than sort | 2025-12-27 | closed

## Sheet2
Logical
User Interface
Maintainability
Standards
Others